## Blad1
Projectnaam	User story #	Work item #	Day 7 - remaining minutes	Day 6	Day 5	Day 4	Day 3	Day 2	Day 1
Sprint 1	User story 1	1.1 - Make a start screen.	80	80	60	40	20	10	0	Make sure you fill in "hours remaining"
Sprint 1	User story 1	1.2 - Put HR logo in start screen.	10	10	10	10	10	5	0
Sprint 1	User story 1	1.3 - Put credits in of the people who worked on the app.	4	4	4	4	4	0	0
Sprint 1	User story 1	1.4 - Put app title in start screen.	6	6	6	6	6	6	0
Sprint 1	User story 1	1.5 - Display start screen in app.	20	20	20	20	10	5	0
Sprint 1	User story 2	2.1 - Make a map of Rotterdam.	30	30	30	30	20	10	0
Sprint 1	User story 2	2.2 - Display map in app.	30	30	30	30	30	20	0
Sprint 1	User story 6	6.1 - Create database.	60	60	40	30	20	10	0
Sprint 1	User story 6	6.2 - Connect database with app.	30	30	30	30	30	20	0

		Ideal	240	200	160	120	80	40	0
		Actual	240	240	200	170	120	61	0

	Burndown Chart / Time in Days / Remaining Minutes (Studypoints)

		Dit is nog van vorig project*