## Blad1
Projectnaam	User story #	Work item #	Day 7 - remaining hours	Day 6	Day 5	Day 4	Day 3	Day 2	Day 1
Sprint 3	User story 7	7.1 Create actions in the game.	6	6	3	3	2	1	0	Make sure you fill in "hours remaining"
Sprint 3	User story 7	7.2 - Put actions in the game.	4	4	3	2	2	1	0
Sprint 3	User story 12	12.1 - Create a 'victory' screen.	1	1	1	0	0	0	0
Sprint 3	User story 12	12.2 - Put a 'Victory' screen in game.	1	1	1	1	0	0	0
Sprint 3	User story 15	15.1 - Create sound effects.	3	3	2	2	2	1	0
Sprint 3	User story 15	15,2 - Put sound effects in game with corresponding actions.	4	4	4	2	2	1	0
Sprint 3	User story 17	17.1 - Create settings button.	4	4	4	3	2	1	0
Sprint 3	User story 17	17.2 - Create settings layout.	1	1	0	0	0	0	0
Sprint 3	User story 17	17.3 - Create background options.	4	4	4	4	3	2	0
Sprint 3	User story 17	17.4 - Put options in the 'settings'.	4	4	4	4	3	2	0

		Ideal	32	26	20	14	9	4	0
		Actual	32	32	26	21	16	9	0

	Burndown Chart / Time in Days

		Dit is nog van vorig project*