## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Priority | Sprint 1 | Sprint 2 | Sprint 3
1 | Create Data Graphs | M |  |  | To Do
2 | Create Home Screen | M |  |  | To Do
3 | Create GUI | M |  |  | To Do
4 | Create Database | M |  |  | To Do
5 | Implement Database in code | M |  |  | To Do
6 | Create Storyboard | M |  |  | To Do
7 | Database containing the info the app uses. | M |  |  | To Do
8 | Make a Back button | M |  |  | To Do
9 | Make a Quit button | M |  |  | To Do

## SPRINT_3_BACKLOG
SPRINT 3 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a user I want to have graphs about Parking lots and P & Rs in Rotterdam so that I know how much space there is and what the information about them is. | M | Whole week | - Make Graphs in code - Put Graphs in app | - The Graphs tell you how much parking space there is from the database. - The Graphs are operable.
2 | As a user I want to have a Home Screen so that I have an orientation point. | M | Whole week | - Make Home Screen - Put Home Screen in app | - The Home Screen must contain 2 Graphs(one for Parking lots and the other for P & Rs - The Home Screen is operable.
3 | As a user I want to have a GUI so that the app is appealing to the eye. | M | Whole week | - Make a GUI from Storyboard - Put GUI in app | - The GUI is user friendly (let 3 people test it.)
4 | As a user I want to have a database so that it can contain information about Parking lots and P & Rs. | M | Whole week | - Create database | - The database has no errors
5 | As a user I want the database to be implemented in the code so that it can give information to the app. | M | Whole week | - Put database in app | - The code has no errors
6 | As a product owner i want to have a visualisation of the application's interface. | M | Whole week | - Make storyboard | - The storyboard must be appealing to the eye
7 | As a user i want to have data from confirmed sources in the application. | M | Whole week | - Put data in database | - The data is correct - The queries are correct
8 | As a user i want to be able to go back to the previous page. | M | Whole week | - Make a Back function - Put Back button in app | - The Back button is operable
9 | As a user i want to have the option to exit the application when i want too. | M | Whole week | - Make a Quit function - Put Quit button in app | - The Quit button is operable