## Blad1
Projectnaam | User story # | Work item # | Day 7 - remaining hours | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Sprint 3 | User story 1 | 1.1 - Make Graphs in code | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Make sure you fill in "hours remaining"
Sprint 3 | User story 1 | 1.2 - Put Graphs in app | 1 | 1 | 1 | 1 | 1 | 1 | 0
Sprint 3 | User story 2 | 2.1 - Make Home Screen | 2 | 2 | 2 | 1 | 1 | 1 | 0
Sprint 3 | User story 3 | 3.1 - Make a GUI and put it in app | 3 | 3 | 3 | 2 | 2 | 1 | 0
Sprint 3 | User story 4 | 4.1 - Create database | 5 | 4 | 3 | 2 | 1 | 1 | 0
Sprint 3 | User story 5 | 5.1 - Put database in app | 4 | 4 | 4 | 3 | 2 | 1 | 0
Sprint 3 | User story 6 | 6.1 - Make storyboard | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 3 | User story 7 | 7.1 - Insert data in database | 1 | 1 | 1 | 1 | 1 | 0 | 0
Sprint 3 | User story 8 | 8.1 Make a back function | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 3 | User story 8 | 8.2 - Put back button in app | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 3 | User story 9 | 9.1 - Make a quit function | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 3 | User story 9 | 9.2 - Put quit button in app | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | Ideal | 23 | 20 | 16 | 12 | 8 | 3 | 0
|  | Actual | 23 | 22 | 17 | 13 | 9 | 5 | 0