## PRODUCT_BACKLOG
Product Backlog
ID	Feature	Priority	Sprint 1	Sprint 2	Sprint 3
1	The app has a start screen.	M	Doing
2	The app has a map from the city Rotterdam.	M	Doing
3	Have a back to map button.	M		To Do
4	Have a quit button which closes the app.	M		To Do
5	Show parking lots and park and rides on the map.	M		To Do
6	Database containing the info the app uses.	M	Doing
7	Parking lots are interactive. (You can click on them)	M
8	Information about parking lots on a new window.	M
9	Create user UI.	M
10	Make the UI User Friendly.	M
11	The app has a search function.	C
12	Map is zoomable.	C
13	UML Use Case.	W
14	Activity Diagram.	W
15	Have a menu option.	W
16	The app has a menu screen.	W
17
18
19
20
21
22
23
24

## SPRINT_1_BACKLOG
SPRINT 1 BACKLOG
ID	User story	Priority	Time Estimation	Tasks	Acceptance criteria
1	As a user I want to have a start screen so that I know which app I am using.	M	1 hour	- Make a start screen. / - Put HR logo in start screen. / - Put credits in of the people who worked on the app. / - Put app title in start screen. / - Display start screen in app.	- The start screen is operable. / - The start screen is a splash screen.
2	As a user I want to see the map of Rotterdam so that I know where to find the parking lots and park and rides.	M	1 hour	- Make a map of Rotterdam. / - Display map in app.	- The map must be the most recent model of Rotterdam. / - The map is accurate to Rotterdam.
6	As a user I want the app to have a database of the data about parking lots and park and rides of Rotterdam so that the app gives me information about it.	M	1 hour	- Create database. / - Connect database with app.	- The database must contain the data about parking lots and park and rides in Rotterdam. / - The data is correct.

## SPRINT_2_BACKLOG
SPRINT 2 BACKLOG
ID	User story	Priority	Time Estimation	Tasks	Acceptance criteria
3	As a user I want a back to map button so that I want go back to the map with one button.	M	1 hour	- Create back to map function. / - Put back to map function in app as back to map button.	- The back to map function is operable.
4	As a user I want a quit button so that I want quit and exit the app.	M	30 min - 1 hour	- Create quit function. / - Put quit function in app as quit button.	- The quit function is operable.
5	As a user I want the parking lots and park and rides to be shown on the map so that I know where they are in Rotterdam.	M	1 - 2 hours	- Use database to pinpoint the location of the parking lots and park and rides. / - Put cooridinates in the map.	- The data shows the exact and correct cooridinates of the parking lots and park and rides.

## SPRINT_3_BACKLOG
SPRINT 3 BACKLOG
ID	User story	Priority	Time Estimation	Tasks	Acceptance criteria